## Sheet1
Semester V | [26 empty] | Semester V
| June |  | July |  |  |  | August |  |  | September |  |  | October |  | November |  | January |  |  |  | Feburary |  |  |  | March
Activities | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Project Idea Finalization | bar: June W2
Requirements | bar: October W13 to October W14
Survey of data/ need (Literature Review) | bar: July W4
Feasibility and need validation | bar: July W4
Scope Freezing | bar: July W5
Requirements Detailing
Use Case Diagrams | bar: July W5
Static User Interface Prototype | bar: July W6
Design
Database Design/ Block Diagram (ER Diagram, Key Data Structures)
Other UML Diagrams (Sequence, Activity, Flow Chart etc.) | bar: August W8
Class Diagrams | bar: August W9
Hardware Design - [for embedded/ IoT projects] | bar: September W11 to September W12
Evaluate Technology options
Prototype
Key Technical issue defination | bar: September W12
Build basic Working Prototype | bar: October W14 to November W2
Planning & Review | bar: October W14
Overall Project Plan | bar: June W1 to July W3
Weekly Review/ Discussion with Guide | bar: June W2; July W4; July W6 to August W8; September W10; September W12 to October W14; November W2
Semester VI
Implementation
Table Creation (if back-end database)
Module 1 | bar: June W1
Development
Unit Testing
Module 2
Development
Unit Testing
System Testing
Test case creation
Intergration Testing
Acceptance Testing
Planning & Review
Overall Project Plan
Weekly Review/ Discussion with Guide